Notes of meeting held on 3rd March 2010 at 11:30 am

Government office for London

| Attending: Christine Parsloe (Chair, LB Merton), Sue Thiedeman (CSIM), Tina Morton (MLAL/LCIP), Toni Ainge (Bexley) ,Tony Leach (London Parks & Green Spaces Forum), Veronica Howe (MLAL), Louise Venn (ACEL), Nigel Foxall (Lee Valley Regional Park Authority), Francis McParland (LB Merton), Joel Brookfield (SE London), Pauline Scott-Garrett (LB Croydon), Sarah Murray (LCIP), Rosemary Doyle (LB Islington), Jon Armstrong (LB Lambeth), Lorraine Lynch (LB Lambeth), Thorsten Dryer (LB Tower Hamlets), Chris Ruse (LB Wandsworth), John McMahon (LCIP) |
| --- |
| Key issues raised | Action |
| 1. Welcome and Introductions Christine Parsloe |  |
| 2. Minutes of last meeting (1 Dec 09) and matters arising Christine Parsloe Agreed ST has liaised with Paul Warren regarding Community of Practice London Parks Forum. ST presented and was well attended. June 18th open meeting, Hillingdon. 15th July City hall event for new portfolio holders | ST to circulate performance managers list TL to write up and circulate |
| 3. London Cultural Improvement Programme – update Sue Theideman/Tina Morton Presentation available at: http://www.londoncouncils.gov.uk/London%20Councils/LCIPProgressmarch2010%5B1%5D.ppt Data review: GREEN Consultation on draft report and recommendations underway Discussion with other RCIG Discussion of next steps & action plan Focus group for LA peers DCMS CASE review report due for publication Impact and outcome measures: GREEN 12 Boroughs participated in training programme so far Tranche 2 training started in Feb Tranche 3 to be advertised soon – June/Sept 2010 1:2:1 support for boroughs successful On line training programme and web tools in development - to be peer tested March 18 2010 Drop out rate relatively high CSIT/Peer Lead Challenge: GREEN Tranches at various stages Final tranche due to complete by April 2010 Currently monitoring status of each boroughs progress Analysis and strategic view of improvement plans underway to inform further bid to Capital Ambition Discussion will be held with CLOA Museum Improvement programme: GREEN Museums Improvement Network now established Tranche 1 Boroughs have begun to share good practice as improvement projects are implemented Tranche 2 well underway, Improvement Planning training Nov 09 £60 – 70K improvement Pot for Improvements 2009 – 11 Advocacy: GREEN November - I&DeA Members Leadership Academy in partnership with Lewisham – only one member from London 1 December – Library Change Programme Members briefing Member Champions confirmed Refocusing due to elections Production of case study materials to support commissioning model rather than events – starting with Children’s Services Library Change Programme: GREEN Capital Ambition agreed £25OK for project team and business modelling dependant on the following: Identify a lead Borough to host the project team Refresh the London Library Change Programme Board Agree a communications plan to manage the messages of this complex change programme to a range of stakeholders in the context of political change at national and local level. New interim project manager Brian Woodcock Working with Children’s Services: GREEN Project underway Project board assembled, first meeting Jan 2010 Case-studies planned Second LAA CYPS training day planned for 18 March 2010 due to demand Heritage Change Programme: AMBER Internal partners meetings held October/November 09 Stakeholder mapping currently taking place Planned stakeholder engagement and brief development for mid March London Events Network and Training: GREEN New improvement network meeting held 1 October (next meeting March 10) Needs analysis/mapping project Interim report presented Planning meeting for peer to peer mentoring, bespoke software and events toolkit progressing Marketing Culture for the Visitor Economy: GREEN Very successful marketing workshop held at Visit London 18th Nov 09 was over subscribed Second marketing workshop held on 27 Jan 10 due to overwhelming demand Bespoke workshop designed for sports development Planning underway for training workshops and online guides Improving Fundraising Capability: AMBER Meeting with Arts and business Scoping and brief development planned for March 2010 Nominees for project team Croydon - economic development company – links to business development. Should look at having a private company on the steering group FilmApp: GREEN Capital Ambition funding: £17k Consortium of Borough Film Offices partners Film London and Visit London Develop online film / broadcasting applications Increase film days Boost Local Economy More efficient processes Link to 2012 Project Management: RED Programme team posts secure to March 2011 Funding gap still exists Sarah Murray recruited to Project Co-ordinator post recruited to start March 2010 Need for posts and project will need to be reviewed nearer to 2011 English Heritage now contributing £15K IDeA contributed £5K | St to look at reasons for drop out |
| 3.b. CSIT analysis Veronica Howe Presentation available at: http://www.londoncouncils.gov.uk/London%20Councils/presentationforCLOAandLCIG2March10%20%282%29.ppt 29 boroughs have undergone CSIT/TAES So far we have records of 15 self assessments, 11 peer reviews and 4 improvement plans Analysis based on 15 boroughs Still incomplete, more evidence needed to inform next phase Climate has changed over 18 months since process began JMcM:Need to ensure CSIT is harnessed to make sure Culture in on the front foot re: Total Place CSIT needs to become more outward facing. NEXT STEPS: sharing case studies; fundamental transformation; partnerships; green flags; PSG: Total Place approach to a particular place or theme is a fundamental change in the way services are provided and funded. New models of working, new philosophy. Need for geographical/partnerships/public sector/outsourcing to be explored. Shared services, joined up working. | ALL to ensure Improvement Plans and accompanying paperwork has been submitted ST: To be included on June Agenda |
| 4. Demonstration - Interactive Best Practice Map Sarah Murray Map to be up on LCIP website soon. Could this include a BLOG or forum? Top 6 topic and word searches to be available. | ALL to submit case study ideas |
| 5. Culture and Sport’s Position within the CAA Sarah Murray CAA Green Flag/ Red Flag analysis |  |
| 6. AOB JB: Place available on Active people diagnostic March 11th TL: Audit happening into volunteering in parks and open spaces. TA: BBC report on public sector cuts. |  |
| Dates of the next meetings: 1 June London Councils September – date and venue TBC 7 December London Councils | CH ST CH |